## Slide 1: PowerPoint 25: Working safely within timescales
PowerPoint presentation
Unit 107: Working with brick, block and stone

## Slide 2: Timescales
All construction projects must keep to timescales, deadlines and budgets to be successful, and the bricklayer has a role in this.
Planning carefully is key to efficiency and productivity on site.
A Gantt chart is a document that helps site personnel follow a set sequence of activities and that shows clearly if work on site is progressing to schedule.
It can be simple or more complex, depending on the size of the project.
 | Task | Week no | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 | 
 | Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | Site preparation and setting out |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Excavation/concrete to foundations and drains |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Brickwork to DPC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Back fill and ram |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Hardcore and ground floor slab |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Brickwork to first lift |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Scaffolding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8 | Brickwork to first floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9 | First floor joisting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10 | Brickwork to eaves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11 | Roof structure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12 | Roof tile |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13 | Windows fitted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14 | Carpentry first fix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
15 | Plumbing first fix/second fix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
16 | Electrical first fix/second fix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
17 | Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
18 | Plastering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
19 | Second fix carpentry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
20 | Decoration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
21 | External finishing/snagging |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Labour requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Labourer |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 
 | Carpenter |  | 1 | 1 |  |  |  |  |  |  |  | 2 |  |  | 2 | 2 | 3 | 3 | 3 | 3 | 3 |  |  | 2 | 2 | 2 | 2 |  | 1 | 1 |  | 
 | Bricklayer |  |  |  | 2 | 2 | 2 | 2 |  | 4 | 4 | 4 | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Subcontractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Scaffolding, roof tiler, services, plumber, electrician, plasterer, painter and decorater, landscaper. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Plant requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Ground works plant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cement mixer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Scaffolding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3: Timescales continued
To contribute to the success of the construction team when working within project timescales, the bricklayer must demonstrate a number of qualities.
  Reliability. Arriving on site at the agreed time and working as instructed.
  Flexibility. Being willing to make changes in work patterns to overcome problems.
  Cooperation. Working alongside other trades and promoting the smooth running of the project.

## Slide 4: Safe working practice
When working on site there are many potential hazards that must be carefully managed.
A great deal of regulation has been developed to protect workers and keep them safe, and inspectors visit construction sites to make sure the law is upheld.
While working within timescales is important, never trade productivity for safety.
Always look for ways to work efficiently but safely, looking after your own welfare and the safety of others working with you.

## Slide 5
Any questions?